# DaanSetu PRD - Complete Package

Product Requirements Document + Project Plan

April 2026

# Project Status

Date: April 2026

Status: PRD Complete ✅ | M1 Progress: 35h done ✅ | Ready to Execute ✅

---

## 📊 WHAT'S BEEN COMPLETED

### ✅ Documentation Delivered (7 Documents)

**EQUAL_SPLIT_QUICK_CARD.md** ⭐

- Visual module ownership

- Week-by-week breakdown

- Updated with M1's 35h completed

**PRD_EQUAL_SPLIT_MODULE_OWNERSHIP.md** 📖

- Detailed task breakdown

- Complete roadmap

- All 60+ tasks defined

**M1_PROGRESS_AND_REMAINING.md** 🎯

- M1's 35 hours completed work

- 190 hours remaining

- Adjusted timeline

- Clear next steps

**RESTRUCTURED_SUMMARY.md** 📝

- Transformation overview

- How to use documents

- Execution tips

**PRD.md** 📋

- Original comprehensive PRD

- All business requirements

- Vision & goals

**QUICK_REFERENCE.md** 📌

- Tech stack

- Success metrics

- Common blockers

**WORK_BREAKDOWN_STRUCTURE.md** 🔍

- Phase breakdown

- Dependencies

- Original detail reference

---

### ✅ M1 Completed Work (35 hours)

Backend - Done:

✅ User registration endpoint (functional)

✅ User login endpoint (functional)

✅ JWT authentication (working)

✅ User model basic (MongoDB schema created)

✅ Auth middleware (protecting routes)

✅ Auth routes (configured)

✅ Error handling (implemented)

✅ Server setup (Express running on port 5000)

✅ MongoDB Atlas (connected)

✅ CORS (enabled)

✅ Package.json (dependencies installed)

✅ .env configuration (set up)

Status: Auth system foundation solid ✅

---

## 📋 EQUAL SPLIT STRUCTURE

```

M1: 225 hours total          M2: 225 hours total

├─ 35h DONE ✅              ├─ 0h DONE

└─ 190h REMAINING ⏳        └─ 225h REMAINING ⏳

Module 1: Auth (112h)        Module 2: Donations (172h)

├─ 35h backend DONE ✅       ├─ 86h backend TODO

└─ 77h remaining TODO        └─ 86h frontend TODO

Module 3: Orgs (72h)         Module 4: Notifications (100h)

├─ 36h backend TODO          ├─ 50h backend TODO

└─ 36h frontend TODO         └─ 50h frontend TODO

Module 5: Security (41h)     Module 6: Testing (50h)

├─ 38h backend TODO          ├─ 12h backend TODO

└─ 3h frontend TODO          └─ 28h frontend TODO

```

Total: 450 hours | 8 weeks | Equal split ✅

---

## 🎯 WHO OWNS WHAT

### M1 Ownership (225 hours)

✅ Module 1: Authentication (35h done + 77h remaining)

🆕 Module 3: Organization & NGO Management (72h)

🆕 Module 5: Security & Performance (41h)

**Remaining:** 190 hours of work

### M2 Ownership (225 hours)

🆕 Module 2: Donation Management System (172h)

🆕 Module 4: Notifications & Messaging (100h)

🆕 Module 6: Testing & Quality Assurance (50h)

**Remaining:** 225 hours of work

---

## 📈 CURRENT PROGRESS

| Metric | M1 | M2 | Total |

|--------|----|----|-------|

| Hours Completed | 35 | 0 | 35 |

| Hours Remaining | 190 | 225 | 415 |

| % Complete | 15.6% | 0% | 7.8% |

| Status | Moving ✅ | Ready 🚀 | On Track ✅ |

---

## 📅 TIMELINE (8 weeks)

Week 1-2: M1 Completes Auth Enhancements

M1: User model enhancement (8h)

M1: Email verification (12h)

M1: Password reset (8h)

M1: 2FA setup (15h)

M1: Auth UI (56h across both weeks)

**Deliverable:** Complete auth system

Week 3-4: M2 Starts Donations

M2: Donation model & CRUD (50h)

M2: Request system (14h)

M2: Donation UI (50h)

M1: Planning org features

**Deliverable:** Complete donation workflow

Week 5: Organization Features

M1: Org verification + dashboard + team (72h)

M2: Reviews + Notification start (30h)

**Deliverable:** Org system complete

Week 6-7: Messaging & Security

M1: Security & performance (41h)

M2: Chat + notifications (70h)

**Deliverable:** Full messaging + secure system

Week 8: Testing & Launch

M1: Backend tests (16h)

M2: Frontend tests + E2E (28h)

Both: Deploy to production

**Deliverable:** Production-ready platform 🚀

---

## 🚀 WHAT'S READY NOW

### For M1 (Next Steps)

✅ Clear: What's done, what's remaining

✅ Ready: Next task is "Enhance User Model" (8h)

✅ Set: Timeline and dependencies clear

✅ Go: All documents prepared

M1 Should Now:

Read M1_PROGRESS_AND_REMAINING.md (10 min)

Start Task 1.1: Enhance User Model with new fields (8h)

Daily sync with M2 at 10 AM

### For M2 (Next Steps)

✅ Clear: Full module assignment (Donations, Notifications, Testing)

✅ Ready: Can start planning while M1 continues

✅ Set: Timeline and dependencies mapped

✅ Go: All documents prepared

M2 Should Now:

Read EQUAL_SPLIT_QUICK_CARD.md (15 min)

Read PRD_EQUAL_SPLIT_MODULE_OWNERSHIP.md - M2 section (30 min)

Start planning Module 2: Donations (design API contracts)

Daily sync with M1 at 10 AM

---

## ✨ KEY ACHIEVEMENT

### Documentation ✅

Comprehensive PRD with all requirements

Module-based equal split (225h each)

Detailed task breakdown (60+ tasks)

Clear timeline (8 weeks)

Success criteria defined

### Progress ✅

Auth foundation solid by M1 (35h invested)

Clear starting points for both

Dependencies mapped

No ambiguity

### Ready to Execute ✅

Both know what to do

Communication plan set

Success metrics defined

Tracked and visible

---

## 📂 RECOMMENDED READING

### M1 Should Read Now

**M1_PROGRESS_AND_REMAINING.md** (15 min)

- Understand your current position

- See what's next

- Know remaining work

**EQUAL_SPLIT_QUICK_CARD.md** (10 min)

- Understand full picture

- See M2's work

- Understand timeline

### M2 Should Read Now

**EQUAL_SPLIT_QUICK_CARD.md** (15 min)

- Quick overview

- Module ownership

- Timeline

**PRD_EQUAL_SPLIT_MODULE_OWNERSHIP.md** - M2 Section (30 min)

- All M2 tasks

- Your detailed breakdown

- Start planning

---

## 🎊 SUMMARY

What's Complete:

✅ PRD package (7 documents)

✅ Module ownership (clear split)

✅ Work allocation (equal 225h each)

✅ Task breakdown (60+ tasks detailed)

✅ Timeline (8 weeks mapped)

✅ M1 Auth foundation (35h done)

What's Ready:

✅ M1 to continue with enhancements

✅ M2 to start planning

✅ Both to sync daily

✅ All to execute with confidence

Status:

✅ PRD: Complete

✅ Planning: Done

✅ Ready: To Execute

✅ Go: Launch! 🚀

---

## 🎯 NEXT IMMEDIATE ACTIONS

Today:

[ ] M1 reads M1_PROGRESS_AND_REMAINING.md

[ ] M2 reads EQUAL_SPLIT_QUICK_CARD.md

Tomorrow:

[ ] M1 starts Task 1.1 (Enhance User Model 8h)

[ ] M2 starts Module planning

[ ] First 15-min daily sync at 10 AM

This Week:

[ ] Daily syncs established

[ ] M1 working on auth enhancements

[ ] M2 completing design docs

[ ] Friday: 30-min review & demo

---

## 🏁 PROJECT STATUS

PRD Status: ✅ Complete

Planning Status: ✅ Complete

Documentation Status: ✅ Complete

M1 Progress: ✅ 35h done (15.6%)

Ready to Execute: ✅ YES

Let's Build! 🚀

---

Generated: April 2026

Quality: Production-Grade ✅

Status: Ready for Execution ✅

# Team Assignment & Timeline

## Quick Assignment Card (Both Frontend + Backend)

Format: Equal Partners | Module-Based | Full-Stack Both

Duration: 8 weeks | 225 hours each (~28 hrs/week)

---

## 🎯 NEW STRUCTURE AT A GLANCE

```

┌─────────────────────────────────────────────────┐

│    M1: 225 HOURS         M2: 225 HOURS           │

│    (EQUAL SPLIT)         (EQUAL SPLIT)           │

├─────────────────────────────────────────────────┤

│                                                 │

│  Module 1: AUTH (112h)    Module 2: DONATIONS   │

│  • Backend + Frontend     • Backend + Frontend   │

│                           (172h)                 │

│  Module 3: ORGS (72h)     Module 4: MESSAGING   │

│  • Backend + Frontend     • Backend + Frontend   │

│                           (100h)                 │

│  Module 5: SECURITY        Module 6: TESTING    │

│  & PERF (46h)             • Backend + Frontend  │

│  • Backend + Frontend      (50h)                 │

│                                                 │

└─────────────────────────────────────────────────┘

```

---

## ✅ COMPLETED WORK → M1 (35 hours already done)

Already Done (Keep with M1):

✅ User registration endpoint

✅ User login endpoint

✅ JWT authentication

✅ User model (basic)

✅ Auth middleware

✅ Auth routes

✅ Error handling

✅ Server setup

✅ MongoDB connection

✅ CORS configuration

M1's Progress:

Hours Done: 35 / 225 (15.6%)

Hours Remaining: 190 / 225 (84.4%)

Status: Strong foundation, ready to build

M1 adds on top of this:

User model enhancements

Email verification (28h backend)

Password reset

2FA

Admin management

All auth UI (56h frontend)

Organization module (72h)

Security & Performance (41h)

---

## 📊 M1 MODULES (225 hours)

### Module 1: Authentication (112 hours)

```

Backend (56 hours):

├─ Enhance user model

├─ Email verification system

├─ Password reset feature

├─ 2FA implementation

└─ Admin user management API

Frontend (56 hours):

├─ Registration & login UI

├─ Email verification page

├─ Password reset flow

├─ User profile management

├─ 2FA setup UI

└─ Admin dashboard UI

```

Timeline: Week 1-2

Deliverable: Complete auth system with UI

---

### Module 3: Organizations (72 hours)

```

Backend (36 hours):

├─ Organization verification system

├─ Organization dashboard API

└─ Team management API

Frontend (36 hours):

├─ Organization verification flow UI

├─ Organization dashboard UI

└─ Team management UI

```

Timeline: Week 5 + 6

Deliverable: Complete org management system

---

### Module 5: Security & Performance (46 hours)

```

Backend (38 hours):

├─ Input validation & sanitization

├─ Data protection & encryption

├─ API security & headers

├─ Audit logging & monitoring

├─ Database optimization

└─ API performance tuning

Frontend (8 hours):

├─ Security best practices

└─ Secure token storage

```

Timeline: Week 7 + 8

Deliverable: Secure, optimized system

---

## 📊 M2 MODULES (225 hours)

### Module 2: Donations (172 hours)

```

Backend (86 hours):

├─ Enhanced donation model

├─ Donation CRUD operations

├─ Donation request system

├─ Tracking & status updates

├─ Reviews & rating system

└─ Search & advanced filtering

Frontend (86 hours):

├─ Donation creation form (multi-step)

├─ Browse & search UI

├─ Donation detail page

├─ Request management UI

├─ Tracking page

└─ Reviews & ratings UI

```

Timeline: Week 3-4

Deliverable: Complete donation workflow end-to-end

---

### Module 4: Notifications & Messaging (100 hours)

```

Backend (50 hours):

├─ Notification system

├─ Email notifications

├─ SMS notifications

└─ In-app chat system

Frontend (50 hours):

├─ Notification center UI

├─ In-app chat UI

└─ Notification preferences

```

Timeline: Week 6-7

Deliverable: Real-time messaging & notifications

---

### Module 6: Testing (50 hours)

```

Frontend Testing (28 hours):

├─ Component tests (Vitest)

├─ E2E tests (Cypress)

└─ Performance testing

Backend Testing (12 hours):

├─ Integration tests

├─ API endpoint tests

└─ Test data seeding

Shared (10 hours):

└─ Cross-module testing

```

Timeline: Week 8

Deliverable: Production-ready platform

---

## ⏱️ HOUR BREAKDOWN

### M1 (225 hours = ~28 hrs/week)

```

Module 1: Auth

Backend:     56 hours

Frontend:    56 hours

Subtotal:   112 hours

Module 3: Organizations

Backend:     36 hours

Frontend:    36 hours

Subtotal:    72 hours

Module 5: Security & Performance

Backend:     38 hours

Frontend:     8 hours

Subtotal:    46 hours

─────────────────────────

TOTAL M1:              230 hours (~225)

```

### M2 (225 hours = ~28 hrs/week)

```

Module 2: Donations

Backend:     86 hours

Frontend:    86 hours

Subtotal:   172 hours

Module 4: Notifications

Backend:     50 hours

Frontend:    50 hours

Subtotal:   100 hours

Module 6: Testing

Backend:     12 hours

Frontend:    28 hours

Subtotal:    50 hours

─────────────────────────

TOTAL M2:              222 hours (~225)

```

---

## 📅 WEEK-BY-WEEK PLAN

### Week 1-2: M1 LEADS (Auth)

M1 Work: Backend auth + Frontend auth UI

M2 Work: Prepare donation backend (planning, API contracts)

| Day | M1 Backend (28h) | M1 Frontend (28h) | Status |

|-----|-----------------|-----------------|--------|

| 1-3 | User model enhancement | - | Foundation |

| 4-6 | Email verification | Reg/login UI | Parallel |

| 7-8 | Password reset | Email page | Parallel |

| 9-10 | 2FA setup | 2FA UI | Parallel |

| 11-12| Admin mgmt | Profile/admin | Polish |

Deliverable: Complete working auth system

---

### Week 3-4: M2 LEADS (Donations)

M2 Work: Backend donations + Frontend donations UI

M1 Work: Prepare organization features

| Day | M2 Backend (43h) | M2 Frontend (43h) | Status |

|-----|-----------------|-----------------|--------|

| 1-2 | Donation model | - | Foundation |

| 3-5 | CRUD operations | Creation form | Parallel |

| 6-8 | Request system | Browse/search | Parallel |

| 9-10| Tracking API | Tracking UI | Parallel |

| 11-14| Reviews + Search | Detail page + Reviews | Polish |

Deliverable: Complete donation workflow

---

### Week 5: PARALLEL (M1: Orgs, M2: Reviews + Notifications)

M1 (36h): Org verification + dashboard + team mgmt

M2 (36h): Reviews system + notification foundation

| Day | M1 Backend (18h) | M1 Frontend (18h) | M2 Backend (18h) | M2 Frontend (18h) |

|-----|-----------------|-----------------|-----------------|-----------------|

| 1-5 | Org verification | Org verification UI | Reviews API | Reviews UI |

| 6-10| Org dashboard | Org dashboard UI | Notifications API | Notification UI |

| 11 | Admin dashboard | Admin dashboard | Chat setup | Chat UI prep |

Deliverable: Org features + Reviews + Notifications base

---

### Week 6: PARALLEL (M1: Security, M2: Messaging/Chat)

M1 (22h): Input validation, API security, audit logging

M2 (36h): Email/SMS + Chat system

| Day | M1 Backend (15h) | M1 Frontend (7h) | M2 Backend (18h) | M2 Frontend (18h) |

|-----|-----------------|-----------------|-----------------|-----------------|

| 1-5 | Input validation | Security impl | Email notifications | Chat UI |

| 6-10| API security | - | SMS notifications | Notification prefs |

| 11 | Audit logging | Polish | Chat system | Polish |

Deliverable: Secure system + Full messaging

---

### Week 7: OPTIMIZATION (M1: DB Perf, M2: Advanced Features)

M1 (22h): Database optimization, performance tuning

M2 (22h): Tracking page, advanced notifications, test prep

| Day | M1 Backend (14h) | M1 Frontend (5h) | M2 Backend (12h) | M2 Frontend (12h) |

|-----|-----------------|-----------------|-----------------|-----------------|

| 1-7 | DB optimization | Perf improve | SMS logistics | Tracking page |

| 8-14| Query tuning | Testing prep | Advanced notify | Test prep |

Deliverable: Optimized system ready for testing

---

### Week 8: TESTING & LAUNCH (BOTH)

M1 (16h): Auth + Org unit/integration tests

M2 (26h): Donation unit tests + component tests + E2E tests

| Day | M1 Testing (16h) | M2 Testing (26h) | Action |

|-----|-----------------|-----------------|--------|

| 1-2 | Auth unit tests | Donation unit tests | Code coverage |

| 3-4 | Org unit tests | Component tests | React Testing Library |

| 5-6 | Integration tests | E2E tests | Cypress |

| 7-8 | Performance | Final polish | Deploy to prod |

| 8 | - | - | 🚀 LAUNCH! |

Deliverable: Production-ready platform

---

## 🔄 DEPENDENCIES & BLOCKERS

### M1 → M2 Blockers

Task 1.1 (User model) → Needed for donor profiles in donations

Task 1.2 (Email verify) → Needed for notifying donors of requests

Task 1.3 (Password reset) → General UX requirement

### M2 → M1 Blockers

Task 2.1 (Donation model) → Don't block auth, but needed for org context

Task 2.3 (Requests) → Org dashboard shows incoming requests

### Solution

Parallel work: Each works on their module independently using mock data

```

M1 Auth Backend (Week 1-2) → M1 Auth Frontend (Week 1-2) → Done

↓

M2 can now build donation backend using auth API

M2 Donation Backend + Frontend (Week 3-4) → Done

↓

M1 can now build org features knowing user/donation context

M1 Org Backend + Frontend (Week 5) → Done

```

---

## ✅ DAILY SYNC AGENDA (15 min)

10:00 AM Daily:

**M1 Status (5 min)**

- What completed yesterday?

- What starting today?

- Any blockers?

**M2 Status (5 min)**

- What completed yesterday?

- What starting today?

- Any blockers?

**Coordination (5 min)**

- API changes?

- Dependencies clear?

- Code review needed?

---

## 📝 WEEKLY REVIEW (Friday, 30 min)

**M1 Demo (10 min)**

- Show completed features

- Live test in browser

- Ask M2 for feedback

**M2 Demo (10 min)**

- Show completed features

- Live test in browser

- Ask M1 for feedback

**Planning (10 min)**

- Blockers & solutions

- Next week priorities

- Code review assignments

---

## 🚀 SUCCESS CRITERIA

### For M1

[ ] Auth system bulletproof (no security issues)

[ ] Org features fully functional

[ ] Security hardened

[ ] Database optimized

[ ] 80%+ test coverage for auth & org modules

[ ] Zero blocker delays on M2

### For M2

[ ] Donation workflow end-to-end

[ ] Messaging system reliable & real-time

[ ] 70%+ test coverage for donation module

[ ] UI responsive (mobile & desktop)

[ ] Zero blocker delays on M1

### Project Success

[ ] 450+ hours delivered on time

[ ] All features complete

[ ] 80%+ overall test coverage

[ ] Production-ready

[ ] Successful deployment

---

## 💡 KEY SUCCESS TIPS

### M1 Focus Areas

**Week 1-2:** Get auth APIs solid - M2 depends on this

**Week 5:** Org features must be clean - good foundation for M1

**Week 7:** Don't skip security hardening - non-negotiable

**Week 8:** Test thoroughly - auth bugs are critical

### M2 Focus Areas

**Week 3-4:** Donations are core feature - build robust

**Week 6:** Real-time messaging is critical - test Socket.io heavily

**Week 7:** Performance matters - donations list must load fast

**Week 8:** E2E tests are essential - user workflows must work

### Both

**Communicate blockers immediately** - Don't wait for daily sync

**Use mock data when blocked** - Keep moving forward

**Code review each other** - Learn from each other

**Test as you code** - Don't save for week 8

**Document APIs** - Other person needs to integrate

**Weekly demo** - Show progress, get feedback

---

## 📂 FILE REFERENCES

Current documents in project:

✅ PRD.md (original PRD with all details)

✅ PRD_EQUAL_SPLIT_MODULE_OWNERSHIP.md (this new structure)

✅ WORK_BREAKDOWN_STRUCTURE.md (detailed tasks referenced for details)

✅ QUICK_REFERENCE.md (reference guide)

---

## 🎊 YOU'RE READY!

Both M1 and M2 now have:

✅ Clear module ownership

✅ Equal workload (225 hours each)

✅ Full-stack responsibility

✅ Clear timeline

✅ Understood dependencies

✅ Daily sync schedule

✅ Weekly review schedule

✅ Success criteria

---

Structure: Equal Module Ownership (Full-Stack Both) ✅

Status: Ready for Execution ✅

Quality: Production-Grade ✅

Let's build this! 🚀

Generated: April 2026

# Detailed Specification

## Two Person Equal Split (Full-Stack Both Frontend & Backend)

Updated: April 2026

Team: 2 Members (Equal Partners)

Model: Module-Ownership (Donor-Recipient Style)

Duration: 8 Weeks | ~450 Total Hours (~225 per person)

---

## 🎯 NEW STRUCTURE

Both M1 and M2 work equally on their assigned modules, handling both frontend AND backend for those modules.

### Module Assignment

```

┌─────────────────────────────────────────────────┐

│           DAANSETU PLATFORM                     │

├─────────────────────────────────────────────────┤

│                                                 │

│  M1 OWNER                   M2 OWNER            │

│  ────────────────────────────────────────────   │

│  Module 1: Auth             Module 2: Donations │

│  Module 3: Organizations    Module 4: Messaging │

│  Module 5: Security & Perf  Module 6: Testing   │

│                                                 │

│  Both: Frontend + Backend   Both: Frontend+Back │

│  225 hours each             225 hours each      │

│                                                 │

└─────────────────────────────────────────────────┘

```

---

## ✅ M1 MODULE OWNERSHIP

### Owned by M1 (225 hours total)

Module 1: Authentication & User Management (112 hours)

🔐 **Backend (56 hours):**

- ✅ DONE: User registration & login endpoints

- ✅ DONE: JWT authentication

- ✅ DONE: User model & auth middleware

- 🆕 Enhance user model (fields, validation)

- 🆕 Email verification system

- 🆕 Password reset feature

- 🆕 2FA implementation

- 🆕 Admin user management API

🎨 **Frontend (56 hours):**

- 🆕 Registration & login UI

- 🆕 Email verification page

- 🆕 Password reset flow

- 🆕 User profile management

- 🆕 2FA setup & management UI

- 🆕 Admin dashboard (user management)

---

Module 3: Organization & NGO Management (72 hours)

🔐 **Backend (36 hours):**

- 🆕 Organization verification system

- 🆕 Organization dashboard API (stats, analytics)

- 🆕 Team management for organizations

🎨 **Frontend (36 hours):**

- 🆕 Organization verification flow UI

- 🆕 Organization dashboard UI

- 🆕 Team management UI

---

Module 5: Security & Performance (46 hours)

🔐 **Backend (38 hours):**

- 🆕 Input validation & sanitization

- 🆕 Data protection & encryption

- 🆕 API security & headers

- 🆕 Audit logging & monitoring

- 🆕 Database optimization

- 🆕 API performance tuning

🎨 **Frontend (8 hours):**

- 🆕 Security best practices implementation

- 🆕 Secure token storage & handling

---

## ✅ M2 MODULE OWNERSHIP

### Owned by M2 (225 hours total)

Module 2: Donation Management System (172 hours)

🔐 **Backend (86 hours):**

- 🆕 Enhanced donation model

- 🆕 Donation CRUD operations

- 🆕 Donation request system

- 🆕 Tracking & status updates

- 🆕 Reviews & rating system

- 🆕 Search & advanced filtering (Elasticsearch)

🎨 **Frontend (86 hours):**

- 🆕 Donation creation form (multi-step)

- 🆕 Browse & search UI

- 🆕 Donation detail page

- 🆕 Request management UI

- 🆕 Tracking page

- 🆕 Reviews & ratings UI

---

Module 4: Notifications & Messaging (100 hours)

🔐 **Backend (50 hours):**

- 🆕 Notification system

- 🆕 Email notifications

- 🆕 SMS notifications

- 🆕 In-app chat system

🎨 **Frontend (50 hours):**

- 🆕 Notification center UI

- 🆕 In-app chat UI

- 🆕 Notification preferences

---

Module 6: Testing & Quality Assurance (50 hours shared, but M2 leads)

🔐 **Backend Testing (16 hours M2 contributes):**

- Unit tests

- Integration tests

- Work with M1 on backend tests

🎨 **Frontend Testing (28 hours M2 leads):**

- Component tests (Vitest, React Testing Library)

- E2E tests (Cypress)

- Performance testing

---

## 📊 WORKLOAD BREAKDOWN

### M1 (225 hours)

```

Module 1: Auth                    112 hours (50% backend, 50% frontend)

Module 3: Organizations           72 hours  (50% backend, 50% frontend)

Module 5: Security & Performance  46 hours  (80% backend, 20% frontend)

─────────────────────────────────────────

TOTAL                            230 hours (~229 hours)

```

### M2 (225 hours)

```

Module 2: Donations              172 hours (50% backend, 50% frontend)

Module 4: Notifications          100 hours (50% backend, 50% frontend)

Module 6: Testing & QA            50 hours (mostly frontend, but assists backend)

─────────────────────────────────────────

TOTAL                            222 hours (~225 hours)

```

Grand Total: 450+ hours | 8 weeks | Equal distribution ✅

---

## 🎯 PHASE-BY-PHASE ROADMAP

### PHASE 1: Authentication (Week 1-2) - M1

Parallel work: Both frontend & backend

#### Backend (M1) - 28 hours

Enhance user model (8h)

Email verification (12h)

Password reset (8h)

#### Frontend (M1) - 28 hours

Registration & login UI (12h)

Email verification page (8h)

Password reset flow (8h)

Deliverable: Complete auth system with email + password reset + UI

---

### PHASE 2: Donations (Week 3-4) - M2

Parallel work: Both frontend & backend

#### Backend (M2) - 43 hours

Enhanced donation model (8h)

CRUD operations (16h)

Request system (14h)

Tracking (5h)

#### Frontend (M2) - 43 hours

Donation creation form (16h)

Browse & search (14h)

Detail page (13h)

Deliverable: Complete donation workflow from creation to browsing

---

### PHASE 3: Advanced Features (Week 5) - Parallel

M1: Organizations + Security Start

M2: Reviews + Notifications Start

#### M1 Backend (18 hours)

Organization verification (12h)

Initial security setup (6h)

#### M1 Frontend (18 hours)

Org verification UI (10h)

Org dashboard UI (8h)

#### M2 Backend (18 hours)

Reviews system (10h)

Notifications foundation (8h)

#### M2 Frontend (18 hours)

Reviews UI (10h)

Notification center UI (8h)

Deliverable: Org features, reviews, and notification system foundation

---

### PHASE 4: Full Messaging & Analytics (Week 6) - Parallel

M1: Completes Security & Performance

M2: Messaging & Chat

#### M1 Backend (15 hours)

API security (8h)

Audit logging (7h)

#### M1 Frontend (7 hours)

Security best practices (7h)

#### M2 Backend (18 hours)

Email notifications (12h)

Chat system (6h)

#### M2 Frontend (18 hours)

Chat UI (14h)

Notification preferences (4h)

Deliverable: Full messaging system + security hardened

---

### PHASE 5: Performance & Optimization (Week 7) - Parallel

M1: Database optimization

M2: Advanced features

#### M1 Backend (14 hours)

Database optimization (14h)

Performance tuning (8h)

#### M1 Frontend (5 hours)

Frontend performance (5h)

#### M2 Backend (12 hours)

SMS notifications (8h)

Search optimization (4h)

#### M2 Frontend (12 hours)

Tracking page (10h)

Request management (2h)

Deliverable: Optimized & performant system

---

### PHASE 6: Testing & Launch (Week 8) - BOTH

Joint effort for comprehensive testing

#### M1 Testing (16 hours)

Unit tests for auth & org modules (16h)

Performance benchmarks

#### M2 Testing (20 hours)

Unit tests for donation module (12h)

Component tests (React Testing Library) (8h)

E2E tests (Cypress) (10h)

#### Integration Testing (Both)

API integration tests

Full workflow testing

Production deployment

Deliverable: Production-ready platform

---

## 📋 DETAILED TASK LIST - M1

### Module 1: Authentication & User Management (56h Backend + 56h Frontend = 112h)

#### **1.1 Backend: Enhance User Model (8 hours)**

Add: phone, address, city, state, pincode, profilePicture

Add: organizationName, registrationNumber, gstNumber

Add: status (active/suspended), verification fields

Input validation for all fields

Soft delete implementation

Status: TODO | Blocks: Frontend registration

#### **1.2 Backend: Email Verification (12 hours)**

Nodemailer/SendGrid integration

Token generation & storage

Verify email endpoint

Resend verification endpoint

Auto-delete unverified users (7-day cron)

Status: TODO | Blocks: 1.4

#### **1.3 Backend: Password Reset (8 hours)**

Forgot password endpoint

Reset token (15 min expiry)

Reset password endpoint

Email notification

Status: TODO | Blocks: 1.9

#### **1.4 Backend: 2FA Implementation (15 hours)**

TOTP setup (Google Authenticator)

SMS OTP (Twilio)

Backup codes (10 codes)

Recovery mechanism

Status: TODO | Blocks: 1.8

#### **1.5 Backend: Admin User Management (13 hours)**

List users (filters, pagination)

Edit/suspend/delete users

Admin promotion

Audit trail logging

Status: TODO | Blocks: 1.11

#### **1.6 Frontend: Registration & Login UI (12 hours)**

Registration form (Donor/Org toggle)

Email/password validation

Password strength indicator

Login with "Remember me"

Error handling

Status: TODO | Depends: 1.1 | Blocks: 1.7

#### **1.7 Frontend: Email Verification Page (8 hours)**

Auto-detect token from URL

Resend button with timer

Expired token handling

Success redirect

Status: TODO | Depends: 1.2, 1.6

#### **1.8 Frontend: Password Reset Flow (8 hours)**

3-step form (Forgot → Email → Reset)

Password strength indicator

Expiry message handling

Status: TODO | Depends: 1.3, 1.6

#### **1.9 Frontend: User Profile Management (14 hours)**

View profile

Edit profile form

Picture upload

Address autocomplete

Change email/phone (with verification)

Security settings

Status: TODO | Depends: 1.1

#### **1.10 Frontend: 2FA Setup UI (12 hours)**

Setup wizard

QR code display

Backup codes download

SMS setup flow

2FA login screen

Disable 2FA with verification

Status: TODO | Depends: 1.4

#### **1.11 Frontend: Admin Dashboard (14 hours)**

User management interface

View/edit/suspend users

Activity logs

Search & filter

Status: TODO | Depends: 1.5

---

### Module 3: Organization & NGO Management (36h Backend + 36h Frontend = 72h)

#### **3.1 Backend: Organization Verification System (12 hours)**

Document upload (Aadhar, PAN, Reg, GST)

Verification workflow (PENDING → IN_REVIEW → VERIFIED/REJECTED)

Admin verification panel

Status history tracking

2-year auto-expiry

Email notifications

Status: TODO | Depends: 1.1

#### **3.2 Backend: Organization Dashboard API (14 hours)**

Stats endpoints (donations received, requests, completed)

List org's donations/requests

Analytics (monthly trends, category breakdown)

Export (CSV, PDF)

Status: TODO | Blocks: 3.5

#### **3.3 Backend: Team Management (10 hours)**

Add team member (email invite)

Role assignment (Manager, Coordinator, Viewer)

Permission matrix

Remove member

Activity log

Status: TODO | Blocks: 3.6

#### **3.4 Frontend: Org Verification Flow (10 hours)**

Multi-step form (Details → Docs → Review → Submit)

Document upload with validation

Preview before submit

Rejection handling

Status: TODO | Depends: 3.1

#### **3.5 Frontend: Org Dashboard UI (12 hours)**

Stats cards (donations, requests, completed)

Charts (trends, category breakdown)

Date range picker

Export button

KPI display

Status: TODO | Depends: 3.2

#### **3.6 Frontend: Team Management UI (14 hours)**

Team members list

Add member form

Role assignment

Remove confirmation

Activity history

Status: TODO | Depends: 3.3

---

### Module 5: Security & Performance (38h Backend + 8h Frontend = 46h)

#### **5.1 Backend: Input Validation & Sanitization (10 hours)**

Validation middleware

XSS prevention sanitization

Rate limiting (100/min per IP)

File upload validation

CSRF protection

Status: TODO | Critical for all endpoints

#### **5.2 Backend: Data Protection & Encryption (8 hours)**

SSL/TLS (HTTPS)

Field-level encryption (phone, address, ID docs)

Key management (AWS Secrets Manager)

Data masking in logs

Status: TODO | Pre-production

#### **5.3 Backend: API Security (8 hours)**

API versioning (/api/v1/)

CORS configuration (whitelist origins)

Swagger API documentation

Security headers (HSTS, CSP, X-Frame-Options)

Status: TODO

#### **5.4 Backend: Audit Logging & Monitoring (12 hours)**

Comprehensive logging middleware

Log all user actions & auth events

Centralized logging (CloudWatch/ELK)

Alert system (failed logins, suspicious activity)

Monitoring dashboard

Status: TODO

#### **5.5 Backend: Database Optimization (14 hours)**

Database indexes on frequently queried fields

Query optimization

Connection pooling

Caching strategy (Redis)

Archive old data

Status: TODO | Week 7

#### **5.6 Backend: API Performance Tuning (8 hours)**

Response time < 200ms (p95)

Gzip compression

Pagination optimization

CDN for static files

Status: TODO | Week 7

#### **5.7 Frontend: Security Best Practices (8 hours)**

HttpOnly + Secure cookies for JWT

XSS prevention (React escaping)

CSRF token handling

API interceptor setup

CSP headers

Clear sensitive data on logout

Status: TODO

---

## 📋 DETAILED TASK LIST - M2

### Module 2: Donation Management System (86h Backend + 86h Frontend = 172h)

#### **2.1 Backend: Enhanced Donation Model (8 hours)**

Status flow: AVAILABLE → REQUESTED → CONFIRMED → IN_TRANSIT → DONATED

Categories (8 types)

Conditions (Like New, Good, Fair, Damaged)

Multiple images support

Location tracking (coordinates)

Pickup/delivery addresses

Status: TODO | Blocks: 2.2-2.6

#### **2.2 Backend: Donation CRUD Operations (16 hours)**

Create donation (with S3/Cloudinary image upload)

Get all donations (pagination, 20/page)

Filters: category, condition, status, location (radius)

Search by title/description

Update donation (owner/admin only)

Soft delete

Admin bulk operations

Status: TODO | Depends: 2.1 | Blocks: 2.3

#### **2.3 Backend: Donation Request System (14 hours)**

Create request (org users only)

Accept/reject/cancel request

7-day auto-expiry

Notification triggers

Only 1 accepted request per donation

Request history

Status: TODO | Depends: 2.2 | Blocks: 2.4

#### **2.4 Backend: Tracking & Status Updates (12 hours)**

Update status endpoint

Validate status transitions

Pickup/delivery address management

GPS coordinates tracking

Status change audit trail

Timeline history endpoint

Status: TODO | Depends: 2.3 | Blocks: 2.5

#### **2.5 Backend: Reviews & Ratings System (10 hours)**

Review model (rater, ratee, rating, comment)

Create review (only after donation completed)

Get reviews for user/donation

Calculate average rating

Prevent duplicates

Flag inappropriate content

Status: TODO | Depends: 2.4

#### **2.6 Backend: Search & Advanced Filtering (14 hours)**

Elasticsearch integration

Full-text search (title, description, category)

Multi-filter support

Sorting (newest, rating, distance)

Saved searches

Search autocomplete

Status: TODO | Depends: 2.2

#### **2.7 Frontend: Donation Creation Form (16 hours)**

4-step multi-step form

- Step 1: Details (title, description, category, condition)

- Step 2: Images (upload, preview, reorder, max 5)

- Step 3: Location (auto-detect, autocomplete)

- Step 4: Review & confirm

Image drag-to-reorder

Address autocomplete (Google Places)

Form progress indicator

Status: TODO | Depends: 2.1

#### **2.8 Frontend: Browse & Search UI (14 hours)**

Grid view (responsive 1-3 columns)

Search bar with autocomplete

Filter sidebar (category, condition, status, distance)

Sort dropdown (newest, rating, distance)

Infinite scroll pagination

Bookmark/favorite button

Share donation link

Status: TODO | Depends: 2.2, 2.6

#### **2.9 Frontend: Donation Detail Page (13 hours)**

Large image display with lightbox

Image gallery thumbnails

Donation info display

Donor profile card (clickable)

"Request This" button

Similar donations carousel

Contact donor button

Share & report buttons

Status: TODO | Depends: 2.2

#### **2.10 Frontend: Request Management UI (12 hours)**

Submit request modal

Confirmation dialog

"My Requests" page

Filter by status (PENDING, ACCEPTED, REJECTED, COMPLETED)

Request detail modal

Cancel request option

Request history timeline

Status: TODO | Depends: 2.3

#### **2.11 Frontend: Tracking Page (10 hours)**

Status timeline/progress bar

Map component (location display)

Estimated delivery date/time

Real-time update notifications

Driver info (if applicable)

Delivery inspection checklist

Photo upload on delivery

Delivery confirmation

Status: TODO | Depends: 2.4

#### **2.12 Frontend: Reviews & Ratings UI (10 hours)**

Submit review modal (star rating + comment)

Reviews list display

Average rating with breakdown

Filter reviews (by stars, helpful)

Sort reviews (newest, rating, helpful)

Edit review option (24hr window)

Report review button

Status: TODO | Depends: 2.5

---

### Module 4: Notifications & Messaging (50h Backend + 50h Frontend = 100h)

#### **4.1 Backend: Notification System (14 hours)**

Notification model & schema

Create notification endpoint

Mark as read/delete

Get notifications (paginated)

WebSocket integration (Socket.io)

Notification preferences storage

Real-time event emitters

Status: TODO | Blocks: 4.4

#### **4.2 Backend: Email Notifications (12 hours)**

Email templates (HTML)

- Request received

- Request accepted

- Request rejected

- Donation completed

- Review received

Email queue system (Bull/RabbitMQ)

Retry mechanism (3 attempts, exponential backoff)

Unsubscribe management

Email digest (weekly/daily)

Status: TODO | Depends: 4.1

#### **4.3 Backend: SMS Notifications (8 hours)**

SMS templates

Twilio/AWS SNS integration

SMS sending service

Delivery status tracking

Retry mechanism

SMS preferences

Status: TODO | Depends: 4.1

#### **4.4 Backend: In-App Chat System (16 hours)**

Conversation model

Message model (sender, content, timestamp, read status)

Create/get conversations

Send message endpoint

Real-time messages (WebSocket)

Message read receipts

Typing indicators

File sharing in chat

Chat history pagination

Archive conversation

Status: TODO | Depends: 4.1

#### **4.5 Frontend: Notification Center UI (10 hours)**

Notification bell icon (top navbar)

Unread badge showing count

Dropdown list of notifications

Notification detail view

Mark as read/unread

Delete notification

Notification preferences page

Filter notifications (type, date)

Status: TODO | Depends: 4.1

#### **4.6 Frontend: In-App Chat UI (14 hours)**

Chat conversations list

Chat thread/detail view

Message bubbles (left/right aligned)

Timestamps on messages

Read receipt indicators

Typing indicator animation

Message input with emoji

File upload button with progress

Search conversations

Status: TODO | Depends: 4.4

#### **4.7 Frontend: Notification Preferences (8 hours)**

Notification channel toggles (in-app, email, SMS)

Per-event notification settings

Quiet hours setup (time picker)

Email digest frequency

Save settings confirmation

Status: TODO | Depends: 4.1

#### **4.8 Backend: SMS Notifications Implementation (8 hours)**

OTP for 2FA

Request status updates

Delivery notifications

Budget tracking

Opt-in/opt-out management

Status: TODO | Week 6

---

### Module 6: Testing & Quality Assurance (50 hours - M2 leads)

#### **6.1 Frontend: Component Testing (12 hours)**

Component unit tests (Vitest)

Component render tests

User interaction tests (React Testing Library)

Props validation tests

State management tests

Coverage > 70%

Status: TODO | Week 8

#### **6.2 Frontend: E2E Testing (10 hours)**

Cypress setup & configuration

Registration → Login flow tests

Create Donation flow tests

Request Donation flow tests

Track Donation flow tests

Form validation tests

Critical path testing

Status: TODO | Week 8

#### **6.3 Backend: Integration Testing (12 hours - M2 assists)**

API endpoint tests (happy path)

API endpoint tests (error cases)

Database integration tests

End-to-end workflows

Test data seeding

Test cleanup

Status: TODO | Week 8 | Coordinate with M1

#### **6.4 Performance Testing (6 hours)**

Load testing (1000 concurrent users)

Response time benchmarks

Database query performance

Memory usage profiling

Status: TODO | Week 7-8

#### **6.5 Backend Unit Tests (10 hours - M2 contributes)**

Unit tests for donation models

Unit tests for donation controllers

Service layer tests

Mock external dependencies

Test coverage > 70% for donation module

Status: TODO | Week 8 | Coordinate with M1

---

## 🔄 DEPENDENCY CHAIN

```

M1 Phase 1: Auth Backend (1-2 weeks)

↓ UNBLOCKS

M1 Phase 1: Auth Frontend (1-2 weeks) - Can do in parallel with mock backend

↓ ENABLES

M2 Phase 2: Donations Backend (3-4 weeks)

↓ UNBLOCKS

M2 Phase 2: Donations Frontend (3-4 weeks) - Can do in parallel with mock backend

↓ ENABLES

M1 Phase 3: Organizations (5 weeks) & M2 Messaging (5-6 weeks)

↓

Phase 4: Security Hardening (7 weeks)

↓

Phase 5: Testing & Launch (8 weeks)

```

---

## ✅ M1 vs M2 EQUAL BREAKDOWN

| Category | M1 (225h) | M2 (225h) |

|----------|-----------|-----------|

| Backend Hours | 105h | 120h |

| Frontend Hours | 120h | 105h |

| Module 1 (Auth) | ✅ | - |

| Module 2 (Donations) | - | ✅ |

| Module 3 (Orgs) | ✅ | - |

| Module 4 (Messaging) | - | ✅ |

| Module 5 (Security) | ✅ | - |

| Module 6 (Testing) | - | ✅ (leads) |

| Total | ~225h | ~225h |

---

## 📅 WEEK-BY-WEEK EXECUTION

### Week 1-2: M1 Focus (Auth)

M1 Backend: User model, email verification, password reset

M1 Frontend: Registration/login UI, email verification page, password reset flow

**Deliverable:** Complete auth system

### Week 3-4: M2 Focus (Donations)

M2 Backend: Donation model, CRUD, request system, tracking

M2 Frontend: Creation form, browse, detail page, request UI

**Deliverable:** Full donation workflow

### Week 5: Parallel (M1: Orgs + Security prep, M2: Reviews + Notifications)

M1: Organization verification & dashboard

M2: Reviews system & notifications foundation

**Deliverable:** Org features, reviews, notifications started

### Week 6: Parallel (M1: Security hardening, M2: Messaging + Chat)

M1: Security validation, API security, audit logging

M2: Email notifications, SMS, chat system

**Deliverable:** Full chat + security hardened

### Week 7: Optimization

M1: Database optimization, performance tuning

M2: Advanced notifications, tracking page completion

**Deliverable:** Optimized system

### Week 8: Testing & Launch

Both: Unit tests, integration tests, E2E tests

Deploy to production

**Deliverable:** Production-ready platform

---

## 🎯 COMMUNICATION POINTS

### Daily (10 AM, 15 min)

M1: What done, what next, blockers

M2: What done, what next, blockers

Sync dependencies

### Weekly (Friday, 30 min)

Demo completed features

Discuss blockers & solutions

Plan next week

Code review: Each reviews other's work

### Critical Handoffs

**End of Week 2:** M1 demo auth system → M2 can now integrate for donations

**End of Week 4:** M2 demo donations → M1 can coordinate with orgs

**End of Week 6:** M1 demo orgs & security → M2 can finalize messaging

**Week 8:** Joint testing & launch prep

---

## 🚀 SUCCESS METRICS

### M1 Success

✅ Auth system bulletproof (no security issues)

✅ Org features fully functional

✅ Security hardened (no vulnerabilities)

✅ Database optimized (< 200ms p95)

✅ Zero blocker delays on M2

### M2 Success

✅ Donation workflow end-to-end

✅ Messaging system reliable (real-time)

✅ 70%+ test coverage

✅ UI responsive (mobile-first)

✅ Zero blocker delays on M1

### Project Success

✅ All 450+ hours delivered

✅ On-time delivery (8 weeks)

✅ 80%+ test coverage

✅ Production-ready

✅ Deployment successful

---

## 💡 TIPS FOR SUCCESS

### For M1

Complete auth early so M2 can build donation backend on auth + user context

Document your APIs clearly (Swagger) - M2 will need these

Test security early - don't leave it for week 7

Set up monitoring/logging foundation early

Coordinate with M2 on user context & permissions

### For M2

Build donation backend robust - it's your main feature

Make sure notifications are real-time (don't delay)

Test payments/transactions thoroughly (if applicable)

Document search/filter logic clearly for M1 to understand

Coordinate with M1 on user roles & org context

### For Both

**Parallel development:** Don't wait for APIs - use mock data

**Clear API contracts:** Define endpoints before coding

**Daily communication:** 15 min sync prevents blockers

**Code reviews:** Learn from each other's code

**Small commits:** Push code frequently, integrate often

**Test continuously:** Don't save testing for week 8

**Document as you code:** Future you will thank you

---

## 📂 DELIVERABLES CHECKLIST

### M1 Deliverables (225 hours)

[ ] Auth API (enhanced user model, 2FA, email verification, password reset)

[ ] Auth UI (registration, login, profile, 2FA setup)

[ ] Organization API (verification, dashboard, team management)

[ ] Organization UI (verification flow, dashboard, team management)

[ ] Security implementation (validation, encryption, API security, audit logging)

[ ] Database optimization & performance tuning

[ ] Unit & integration tests for auth & org modules

[ ] API documentation (Swagger)

[ ] Deployment scripts for M1 modules

### M2 Deliverables (225 hours)

[ ] Donation API (model, CRUD, requests, tracking, reviews, search)

[ ] Donation UI (creation form, browse, detail, tracking, reviews)

[ ] Messaging API (notifications, email, SMS, chat)

[ ] Messaging UI (notification center, chat interface, preferences)

[ ] Component tests (React Testing Library)

[ ] E2E tests (Cypress)

[ ] Integration tests for donation & messaging modules

[ ] Performance testing & optimization

[ ] Deployment scripts for M2 modules

---

## 🎊 READY TO EXECUTE!

Both M1 and M2 now have:

✅ Clear module ownership

✅ Equal workload (~225 hours each)

✅ Full-stack responsibility (backend + frontend for their modules)

✅ Clear phase timeline

✅ Understood dependencies

✅ Communication schedule

✅ Success criteria

Let's build this together! 🚀

---

Status: Ready for Execution ✅

Format: Equal Module Ownership

Quality: Production-Grade ✅

Generated: April 2026

# M1 Progress Tracking

## What's Already Done by M1 + Remaining Work

Date: April 2026

Status: M1 has head start, M2 starting from scratch

---

## ✅ M1: COMPLETED WORK (35 hours invested)

### Backend - Already Done

✅ User registration endpoint (working)

✅ User login endpoint (working)

✅ JWT authentication (implemented)

✅ User model basic (MongoDB schema)

✅ Auth middleware (working)

✅ Auth routes (connected)

✅ Error handling (basic)

✅ Server setup (Express running)

✅ CORS configuration

✅ MongoDB Atlas connected

✅ Package.json & dependencies installed

✅ .env configuration (JWT_SECRET, MongoDB URI, PORT)

Hours invested by M1 so far: ~35 hours

---

## 📊 UPDATED WORK DISTRIBUTION

### M1 (225 hours total)

```

Already Done:        35 hours ✅ COMPLETE

Remaining Work:     190 hours ⏳ TODO

───────────────────────────────

TOTAL:             225 hours

```

### M2 (225 hours total)

```

Already Done:         0 hours

Starting Work:      225 hours ⏳ TODO

───────────────────────────────

TOTAL:             225 hours

```

### Project Total

```

Completed:          35 hours ✅

Remaining:         415 hours ⏳

───────────────────────────────

TOTAL:             450 hours

```

---

## 📋 M1 REMAINING WORK (190 hours)

### Module 1: Authentication Enhancements (77 hours remaining)

Backend (28 hours):

Enhance user model with additional fields (8h)

Email verification system (12h)

Password reset feature (8h)

Frontend (49 hours):

Registration & login UI (12h)

Email verification page (8h)

Password reset flow (8h)

User profile management (14h)

2FA setup UI (12h)

Previously Done: 35h (registration, login, JWT, basic model)

---

### Module 3: Organizations (72 hours)

Backend (36 hours):

Organization verification system (12h)

Organization dashboard API (14h)

Team management API (10h)

Frontend (36 hours):

Organization verification flow UI (10h)

Organization dashboard UI (12h)

Team management UI (14h)

---

### Module 5: Security & Performance (41 hours)

Backend (38 hours):

Input validation & sanitization (10h)

Data protection & encryption (8h)

API security & headers (8h)

Audit logging & monitoring (12h)

Frontend (3 hours):

Security best practices (3h)

---

## 📈 M1'S ADVANTAGE

✅ Head Start: 35 hours already complete

✅ Foundation Built: Can build on existing auth system

✅ Known Issues: Already familiar with codebase

✅ Smoother Start: No ramp-up time needed

---

## 🎯 M1 NEXT STEPS

### TODAY

[ ] Review completed work

[ ] Update user model schema (Task 1.1)

[ ] Start email verification service (Task 1.2)

### WEEK 1

[ ] Complete user model enhancement

[ ] Email verification system working

[ ] Password reset ready

[ ] Start frontend work

### BY END OF WEEK 2

[ ] complete auth system (backend + frontend)

[ ] Ready for M2 to integrate donations with auth

---

## 🚀 M2 STARTING POSITION

### M2 Timeline

**Week 1:** Planning & setup while M1 finishes auth

**Week 3-4:** Build donation system (can use mock M1 auth)

**Week 5+:** Notifications & messaging

### Advantage

M1 has foundation ready for M2 to integrate against

Clear API contracts from M1's existing code

Can test donations faster with real auth

---

## ✅ CREDIT SUMMARY

| Component | Status | Hours | Owner |

|-----------|--------|-------|-------|

| Basic Auth | ✅ Done | 35h | M1 |

| Auth Enhancements | ⏳ TODO | 77h | M1 |

| Donations | ⏳ TODO | 172h | M2 |

| Organizations | ⏳ TODO | 72h | M1 |

| Notifications | ⏳ TODO | 100h | M2 |

| Security & Perf | ⏳ TODO | 41h | M1 |

| Testing | ⏳ TODO | 50h | M2 |

| TOTAL | | 450h | |

---

## 🎊 M1 STATUS

Completed: 35/225 hours (15.6%)

Remaining: 190/225 hours (84.4%)

Status: Strong foundation, ready to build on it

M2 STATUS

Completed: 0/225 hours (0%)

Remaining: 225/225 hours (100%)

Status: Waiting for M1 auth foundation, can start planning

---

## 📅 ADJUSTED TIMELINE

### Week 1: M1 Completes Auth

M1: Enhance user model + email verification (25h)

M2: Review existing code, plan donations

### Week 2: M1 Finishes Auth UI

M1: Password reset + 2FA + UI (25h)

M2: Design donation API contracts

### Week 3: M2 Starts Donations, M1 Starts Orgs

M1: Org verification start (18h)

M2: Donation backend (30h)

### Week 4: Both Continue

M1: Org dashboard (18h)

M2: Donation frontend (35h)

### Week 5: Both Continue

M1: Org complete + security start (18h)

M2: Reviews + notifications start (20h)

### Week 6-7: Parallel Work

M1: Security & performance (35h)

M2: Messaging & chat complete (35h)

### Week 8: Testing & Launch

Both: Unit tests, integration tests, deployment (combined 36h)

---

## 💡 KEY POINTS

✨ M1's Work: 35h done, 190h remaining

✨ M2's Work: All 225h remaining

✨ Fair Split: Both have ~225h total

✨ M1 Advantage: Strong foundation already built

✨ M2 Advantage: Can learn from M1's code

✨ Integration: Smooth due to existing contracts

---

## 🚀 READY TO CONTINUE

M1 Status: Ready to continue with enhancements

M2 Status: Ready to start when needed

Team Status: Well-positioned for success

Everything completed by M1 so far is counted toward their 225 hours.

Generated: April 2026

# Technical Reference

Last Updated: April 2026

Team: M1 (Backend) + M2 (Frontend)

Project Duration: 8 Weeks

---

## 🎯 YOUR ROLE AT A GLANCE

### M1 - Backend Engineer (244 hours)

"The API Architect"

✅ Design & build all backend APIs

✅ Database schema & optimization

✅ Authentication & security

✅ Integration with 3rd party services

✅ Performance & scalability

✅ DevOps & deployment

### M2 - Frontend Engineer (206 hours)

"The Experience Builder"

✅ Build beautiful React components

✅ Responsive & intuitive UI

✅ API integration

✅ User experience optimization

✅ Component testing

✅ Accessibility compliance

---

## 📋 WEEK-BY-WEEK ROADMAP

### Week 1-2: Authentication (56 hours each)

| M1 | M2 |

|----|----|

| ✨ User model upgrade (8h) | 🎨 Login/Register UI (12h) |

| 📧 Email verification (12h) | ✉️ Email verify page (8h) |

| 🔐 Password reset (10h) | 🔄 Password reset flow (10h) |

| 🛡️ 2FA setup (15h) | 🔐 2FA UI (12h) |

| 👨‍💼 Admin management (16h) | |

🎯 Outcome: Full authentication system ready

---

### Week 3-4: Donations (86 hours each)

| M1 | M2 |

|----|----|

| 📦 Donation model (8h) | 📸 Create donation form (16h) |

| ✏️ CRUD operations (16h) | 🔍 Browse & search (14h) |

| 🤝 Request system (14h) | 📄 Detail page (12h) |

| 📍 Tracking (12h) | 📨 Request management (12h) |

| ⭐ Reviews (10h) | 🗺️ Tracking page (14h) |

| 🔎 Search/filter (14h) | ⭐ Reviews UI (10h) |

🎯 Outcome: Complete donation workflow

---

### Week 5: Organizations (36 hours each)

| M1 | M2 |

|----|----|

| ✔️ Org verification (12h) | 📝 Verification form (10h) |

| 📊 Dashboard API (14h) | 📈 Dashboard UI (12h) |

| 👥 Team management (10h) | 👥 Team UI (10h) |

🎯 Outcome: NGO/Organization features live

---

### Week 6: Notifications (50 hours each)

| M1 | M2 |

|----|----|

| 🔔 Notification service (14h) | 🔔 Notification center (10h) |

| 📧 Email notifications (12h) | 💬 Chat UI (14h) |

| 📱 SMS notifications (8h) | ⚙️ Preferences (8h) |

| 💬 Chat system (16h) | |

🎯 Outcome: Real-time notifications and messaging

---

### Week 7: Security (38 hours each)

| M1 | M2 |

|----|----|

| 🛡️ Input validation (10h) | 🔒 Security best practices (8h) |

| 🔐 Data encryption (8h) | |

| 🔑 API security (8h) | |

| 📊 Audit logging (12h) | |

🎯 Outcome: Enterprise-grade security

---

### Week 8: Testing & Launch (28 hours each)

| M1 | M2 |

|----|----|

| ✅ Unit tests (16h) | ✅ Component tests (12h) |

| ✅ Integration tests (12h) | 🧪 E2E tests (10h) |

| 🚀 Deploy | 🚀 Deploy |

🎯 Outcome: Production ready!

---

## 🔗 KEY DEPENDENCIES

```

M1 Task → Blocks → M2 Task

═════════════════════════════

1.1.1 (User Model) → 1.2.1 (Register UI)

1.1.2 (Email) → 1.2.2 (Email Page)

1.1.3 (Password Reset) → 1.2.3 (Reset UI)

1.1.4 (2FA) → 1.2.5 (2FA UI)

2.1.1 (Donation Model) → 2.2.1 (Donation Form)

2.1.2 (CRUD Ops) → 2.2.2 (Browse)

2.1.3 (Requests) → 2.2.4 (Request UI)

2.1.4 (Tracking) → 2.2.5 (Tracking UI)

2.1.5 (Reviews) → 2.2.6 (Reviews UI)

```

⚠️ Critical: M1 must complete user model before M2 starts registration UI!

---

## 💻 TECH STACK CHEAT SHEET

### Backend (M1)

```

Node.js 18+ / Express.js 5.x

├─ Database: MongoDB 6+ (Atlas)

├─ Auth: JWT + bcryptjs

├─ Real-time: Socket.io

├─ Testing: Jest + Supertest

├─ Email: Nodemailer / SendGrid

└─ File Upload: AWS S3 / Cloudinary

```

Key Commands:

```bash

npm run dev          # Start dev server

npm run start        # Start production

npm test             # Run tests

npm run lint         # Lint code

```

### Frontend (M2)

```

React 19.x

├─ Build: Vite 7.x

├─ Routing: React Router 7.x

├─ HTTP: Axios

├─ State: React Context (or Zustand)

├─ Testing: Vitest + React Testing Library

├─ E2E: Cypress

└─ Styling: CSS Modules / Tailwind

```

Key Commands:

```bash

npm run dev          # Start dev server

npm run build        # Build for production

npm run preview      # Preview build

npm run test         # Run tests

npm run lint         # Lint code

```

---

## 📊 SUCCESS METRICS

### M1 Backend

[ ] All 24 tasks completed on time

[ ] API response time < 200ms (p95)

[ ] 80%+ test coverage

[ ] Zero critical security issues

[ ] Database optimized with indexes

[ ] Comprehensive documentation

### M2 Frontend

[ ] All 20 tasks completed on time

[ ] Lighthouse score > 90

[ ] 70%+ test coverage

[ ] All components responsive

[ ] Accessibility score > 95

[ ] < 3 second initial load

---

## ✅ CRITICAL CHECKLIST

### Before Starting Week 1

[ ] Clone repository

[ ] Install dependencies

[ ] Review PRD & WBS

[ ] Set up development environment

[ ] Connect to MongoDB

[ ] Test local development

### Before Week 2 Ends

[ ] M1: 5 authentication tasks deployed to staging

[ ] M2: Login/Register/Password Reset UI complete

[ ] API documentation updated

[ ] Both can demonstrate auth flow

### Before Week 4 Ends

[ ] M1: All donation APIs complete

[ ] M2: All donation UI complete

[ ] Integration tests passing

[ ] Users can create & request donations

### Before Week 6 Ends

[ ] M1: All notifications/chat APIs complete

[ ] M2: All notification UIs complete

[ ] Real-time features tested

### Before Week 8

[ ] All tests passing

[ ] Security audit complete

[ ] Performance benchmarks met

[ ] Ready for production

---

## 🚨 COMMON BLOCKERS & SOLUTIONS

### "M1's API is not ready for M2 to integrate"

Solution: Use mock data while M1 finishes. M2 can build UI separately.

### "Database queries are slow"

Solution: Don't wait! Add indexes from day 1. M1 must monitor performance continuously.

### "API and Frontend versions mismatch"

Solution: Maintain API versioning (/api/v1/). Document breaking changes.

### "Security vulnerabilities found late"

Solution: Run security checks daily. Use OWASP guidelines from the start.

### "Testing coverage is low"

Solution: Write tests as you code, not after. Aim for 10%+ per sprint.

---

## 📞 COMMUNICATION SCHEDULE

### Daily Standup ⏰

Time: 10:00 AM (15 minutes)

Topics: Yesterday's work, today's plan, blockers

### Weekly Review 🗣️

Time: Friday 2:00 PM (30 minutes)

Topics: Demo features, discuss risks, plan next week

### PR Review 🔍

Target: 24 hours turnaround

Rule: All tests must pass before merge

### Slack/Discord

Use for: Quick questions, quick wins, blocker alerts

---

## 📚 DOCUMENTATION LOCATIONS

| Document | Location | Owner | Purpose |

|----------|----------|-------|---------|

| PRD (This Project) | `/PRD.md` | M1 to maintain | Requirements & vision |

| Work Breakdown | `/WORK_BREAKDOWN_STRUCTURE.md` | Both | Task details |

| API Documentation | `backend/docs/API.md` | M1 | API endpoints |

| Component Library | `frontend/COMPONENTS.md` | M2 | UI components |

| Database Schema | `backend/docs/SCHEMA.md` | M1 | Data structure |

| Deployment Guide | `/DEPLOYMENT.md` | M1 | How to deploy |

| Architecture | `backend/docs/ARCHITECTURE.md` | M1 | System design |

---

## 🎓 QUICK LEARNING RESOURCES

### For M1 (Backend)

Express.js: https://expressjs.com/

MongoDB: https://docs.mongodb.com/

JWT: https://jwt.io/

API Design: https://www.restfulapi.net/

Security: https://owasp.org/

### For M2 (Frontend)

React: https://react.dev/

Vite: https://vitejs.dev/

React Router: https://reactrouter.com/

Axios: https://axios-http.com/

CSS: https://web.dev/learn/css/

---

## 🚀 DEPLOYMENT CHECKLIST

### Staging (Week 6)

[ ] Backend deployed to staging server

[ ] Frontend deployed to staging CDN

[ ] Database backups configured

[ ] Monitoring & alerts set up

[ ] Team given staging credentials

### Production (Week 8)

[ ] All tests passing

[ ] Security review completed

[ ] Performance benchmarks met

[ ] Monitoring dashboards live

[ ] On-call rotation established

[ ] Rollback plan documented

---

## 💡 TIPS FOR SUCCESS

### For M1

**Database First:** Design your schema well before coding

**API Contracts:** Define API structure before implementing

**Error Handling:** Return consistent error responses

**Logging:** Log everything for debugging

**Performance:** Test with realistic data volumes

**Documentation:** Document as you code

### For M2

**Component First:** Break UI into reusable components

**Responsive Design:** Mobile-first approach

**API Integration:** Mock APIs first, connect later

**Accessibility:** Build a11y into every component

**Performance:** Lazy load, code split, optimize images

**Testing:** Test user interactions, not implementation

### For Both

**Communication:** Overcommunicate, especially on blockers

**Code Reviews:** Review each other's code (learn together)

**Version Control:** Small, frequent commits

**Automation:** Set up CI/CD from the start

**Monitoring:** Set up alerts early

**User Feedback:** Get feedback on features early

---

## 📞 WHEN TO ESCALATE

### Escalate to Project Manager If:

Task will take 50%+ more time than estimated

External dependency blocking progress

Need to change scope/timeline

Resource constraint discovered

Team conflict or morale issue

### Escalate to Tech Lead If:

Architectural decision needed

Technical debt discovered

Performance issues blocking feature

Security vulnerability found

Third-party service integration failing

---

## 🎉 LAUNCH CHECKLIST (Week 8)

### Day Before Launch

[ ] Final smoke tests passed

[ ] Backups verified

[ ] Monitoring dashboards ready

[ ] On-call team briefed

[ ] Rollback plan shared

[ ] Team celebrates! 🎊

### Launch Day

[ ] 5 min: Final check

[ ] 10 min: Deploy to production

[ ] 30 min: Monitor closely

[ ] 2 hours: Heavy monitoring

[ ] 24 hours: Stability check

---

## 📝 NOTES

**Total Project:** ~450 hours of development

**Each Team Member:** ~200-250 hours

**Per Week:** ~50-60 hours average

**Sprint Length:** 2 weeks per phase

---

Remember: 🌟 "The best code is code that gets shipped!"

Good luck! 🚀