# 🎯 M1 STARTING POSITION

## What's Already Done by M1 + Remaining Work

Date: April 2026

Status: M1 has head start, M2 starting from scratch

---

## ✅ M1: COMPLETED WORK (35 hours invested)

### Backend - Already Done

✅ User registration endpoint (working)

✅ User login endpoint (working)

✅ JWT authentication (implemented)

✅ User model basic (MongoDB schema)

✅ Auth middleware (working)

✅ Auth routes (connected)

✅ Error handling (basic)

✅ Server setup (Express running)

✅ CORS configuration

✅ MongoDB Atlas connected

✅ Package.json & dependencies installed

✅ .env configuration (JWT_SECRET, MongoDB URI, PORT)

Hours invested by M1 so far: ~35 hours

---

## 📊 UPDATED WORK DISTRIBUTION

### M1 (225 hours total)

```

Already Done:        35 hours ✅ COMPLETE

Remaining Work:     190 hours ⏳ TODO

───────────────────────────────

TOTAL:             225 hours

```

### M2 (225 hours total)

```

Already Done:         0 hours

Starting Work:      225 hours ⏳ TODO

───────────────────────────────

TOTAL:             225 hours

```

### Project Total

```

Completed:          35 hours ✅

Remaining:         415 hours ⏳

───────────────────────────────

TOTAL:             450 hours

```

---

## 📋 M1 REMAINING WORK (190 hours)

### Module 1: Authentication Enhancements (77 hours remaining)

Backend (28 hours):

Enhance user model with additional fields (8h)

Email verification system (12h)

Password reset feature (8h)

Frontend (49 hours):

Registration & login UI (12h)

Email verification page (8h)

Password reset flow (8h)

User profile management (14h)

2FA setup UI (12h)

Previously Done: 35h (registration, login, JWT, basic model)

---

### Module 3: Organizations (72 hours)

Backend (36 hours):

Organization verification system (12h)

Organization dashboard API (14h)

Team management API (10h)

Frontend (36 hours):

Organization verification flow UI (10h)

Organization dashboard UI (12h)

Team management UI (14h)

---

### Module 5: Security & Performance (41 hours)

Backend (38 hours):

Input validation & sanitization (10h)

Data protection & encryption (8h)

API security & headers (8h)

Audit logging & monitoring (12h)

Frontend (3 hours):

Security best practices (3h)

---

## 📈 M1'S ADVANTAGE

✅ Head Start: 35 hours already complete

✅ Foundation Built: Can build on existing auth system

✅ Known Issues: Already familiar with codebase

✅ Smoother Start: No ramp-up time needed

---

## 🎯 M1 NEXT STEPS

### TODAY

[ ] Review completed work

[ ] Update user model schema (Task 1.1)

[ ] Start email verification service (Task 1.2)

### WEEK 1

[ ] Complete user model enhancement

[ ] Email verification system working

[ ] Password reset ready

[ ] Start frontend work

### BY END OF WEEK 2

[ ] complete auth system (backend + frontend)

[ ] Ready for M2 to integrate donations with auth

---

## 🚀 M2 STARTING POSITION

### M2 Timeline

**Week 1:** Planning & setup while M1 finishes auth

**Week 3-4:** Build donation system (can use mock M1 auth)

**Week 5+:** Notifications & messaging

### Advantage

M1 has foundation ready for M2 to integrate against

Clear API contracts from M1's existing code

Can test donations faster with real auth

---

## ✅ CREDIT SUMMARY

| Component | Status | Hours | Owner |

|-----------|--------|-------|-------|

| Basic Auth | ✅ Done | 35h | M1 |

| Auth Enhancements | ⏳ TODO | 77h | M1 |

| Donations | ⏳ TODO | 172h | M2 |

| Organizations | ⏳ TODO | 72h | M1 |

| Notifications | ⏳ TODO | 100h | M2 |

| Security & Perf | ⏳ TODO | 41h | M1 |

| Testing | ⏳ TODO | 50h | M2 |

| TOTAL | | 450h | |

---

## 🎊 M1 STATUS

Completed: 35/225 hours (15.6%)

Remaining: 190/225 hours (84.4%)

Status: Strong foundation, ready to build on it

M2 STATUS

Completed: 0/225 hours (0%)

Remaining: 225/225 hours (100%)

Status: Waiting for M1 auth foundation, can start planning

---

## 📅 ADJUSTED TIMELINE

### Week 1: M1 Completes Auth

M1: Enhance user model + email verification (25h)

M2: Review existing code, plan donations

### Week 2: M1 Finishes Auth UI

M1: Password reset + 2FA + UI (25h)

M2: Design donation API contracts

### Week 3: M2 Starts Donations, M1 Starts Orgs

M1: Org verification start (18h)

M2: Donation backend (30h)

### Week 4: Both Continue

M1: Org dashboard (18h)

M2: Donation frontend (35h)

### Week 5: Both Continue

M1: Org complete + security start (18h)

M2: Reviews + notifications start (20h)

### Week 6-7: Parallel Work

M1: Security & performance (35h)

M2: Messaging & chat complete (35h)

### Week 8: Testing & Launch

Both: Unit tests, integration tests, deployment (combined 36h)

---

## 💡 KEY POINTS

✨ M1's Work: 35h done, 190h remaining

✨ M2's Work: All 225h remaining

✨ Fair Split: Both have ~225h total

✨ M1 Advantage: Strong foundation already built

✨ M2 Advantage: Can learn from M1's code

✨ Integration: Smooth due to existing contracts

---

## 🚀 READY TO CONTINUE

M1 Status: Ready to continue with enhancements

M2 Status: Ready to start when needed

Team Status: Well-positioned for success

Everything completed by M1 so far is counted toward their 225 hours.

Generated: April 2026