# DaanSetu - Team Quick Reference Guide

Last Updated: April 2026

Team: M1 (Backend) + M2 (Frontend)

Project Duration: 8 Weeks

---

## 🎯 YOUR ROLE AT A GLANCE

### M1 - Backend Engineer (244 hours)

"The API Architect"

✅ Design & build all backend APIs

✅ Database schema & optimization

✅ Authentication & security

✅ Integration with 3rd party services

✅ Performance & scalability

✅ DevOps & deployment

### M2 - Frontend Engineer (206 hours)

"The Experience Builder"

✅ Build beautiful React components

✅ Responsive & intuitive UI

✅ API integration

✅ User experience optimization

✅ Component testing

✅ Accessibility compliance

---

## 📋 WEEK-BY-WEEK ROADMAP

### Week 1-2: Authentication (56 hours each)

| M1 | M2 |

|----|----|

| ✨ User model upgrade (8h) | 🎨 Login/Register UI (12h) |

| 📧 Email verification (12h) | ✉️ Email verify page (8h) |

| 🔐 Password reset (10h) | 🔄 Password reset flow (10h) |

| 🛡️ 2FA setup (15h) | 🔐 2FA UI (12h) |

| 👨‍💼 Admin management (16h) | |

🎯 Outcome: Full authentication system ready

---

### Week 3-4: Donations (86 hours each)

| M1 | M2 |

|----|----|

| 📦 Donation model (8h) | 📸 Create donation form (16h) |

| ✏️ CRUD operations (16h) | 🔍 Browse & search (14h) |

| 🤝 Request system (14h) | 📄 Detail page (12h) |

| 📍 Tracking (12h) | 📨 Request management (12h) |

| ⭐ Reviews (10h) | 🗺️ Tracking page (14h) |

| 🔎 Search/filter (14h) | ⭐ Reviews UI (10h) |

🎯 Outcome: Complete donation workflow

---

### Week 5: Organizations (36 hours each)

| M1 | M2 |

|----|----|

| ✔️ Org verification (12h) | 📝 Verification form (10h) |

| 📊 Dashboard API (14h) | 📈 Dashboard UI (12h) |

| 👥 Team management (10h) | 👥 Team UI (10h) |

🎯 Outcome: NGO/Organization features live

---

### Week 6: Notifications (50 hours each)

| M1 | M2 |

|----|----|

| 🔔 Notification service (14h) | 🔔 Notification center (10h) |

| 📧 Email notifications (12h) | 💬 Chat UI (14h) |

| 📱 SMS notifications (8h) | ⚙️ Preferences (8h) |

| 💬 Chat system (16h) | |

🎯 Outcome: Real-time notifications and messaging

---

### Week 7: Security (38 hours each)

| M1 | M2 |

|----|----|

| 🛡️ Input validation (10h) | 🔒 Security best practices (8h) |

| 🔐 Data encryption (8h) | |

| 🔑 API security (8h) | |

| 📊 Audit logging (12h) | |

🎯 Outcome: Enterprise-grade security

---

### Week 8: Testing & Launch (28 hours each)

| M1 | M2 |

|----|----|

| ✅ Unit tests (16h) | ✅ Component tests (12h) |

| ✅ Integration tests (12h) | 🧪 E2E tests (10h) |

| 🚀 Deploy | 🚀 Deploy |

🎯 Outcome: Production ready!

---

## 🔗 KEY DEPENDENCIES

```

M1 Task → Blocks → M2 Task

═════════════════════════════

1.1.1 (User Model) → 1.2.1 (Register UI)

1.1.2 (Email) → 1.2.2 (Email Page)

1.1.3 (Password Reset) → 1.2.3 (Reset UI)

1.1.4 (2FA) → 1.2.5 (2FA UI)

2.1.1 (Donation Model) → 2.2.1 (Donation Form)

2.1.2 (CRUD Ops) → 2.2.2 (Browse)

2.1.3 (Requests) → 2.2.4 (Request UI)

2.1.4 (Tracking) → 2.2.5 (Tracking UI)

2.1.5 (Reviews) → 2.2.6 (Reviews UI)

```

⚠️ Critical: M1 must complete user model before M2 starts registration UI!

---

## 💻 TECH STACK CHEAT SHEET

### Backend (M1)

```

Node.js 18+ / Express.js 5.x

├─ Database: MongoDB 6+ (Atlas)

├─ Auth: JWT + bcryptjs

├─ Real-time: Socket.io

├─ Testing: Jest + Supertest

├─ Email: Nodemailer / SendGrid

└─ File Upload: AWS S3 / Cloudinary

```

Key Commands:

```bash

npm run dev          # Start dev server

npm run start        # Start production

npm test             # Run tests

npm run lint         # Lint code

```

### Frontend (M2)

```

React 19.x

├─ Build: Vite 7.x

├─ Routing: React Router 7.x

├─ HTTP: Axios

├─ State: React Context (or Zustand)

├─ Testing: Vitest + React Testing Library

├─ E2E: Cypress

└─ Styling: CSS Modules / Tailwind

```

Key Commands:

```bash

npm run dev          # Start dev server

npm run build        # Build for production

npm run preview      # Preview build

npm run test         # Run tests

npm run lint         # Lint code

```

---

## 📊 SUCCESS METRICS

### M1 Backend

[ ] All 24 tasks completed on time

[ ] API response time < 200ms (p95)

[ ] 80%+ test coverage

[ ] Zero critical security issues

[ ] Database optimized with indexes

[ ] Comprehensive documentation

### M2 Frontend

[ ] All 20 tasks completed on time

[ ] Lighthouse score > 90

[ ] 70%+ test coverage

[ ] All components responsive

[ ] Accessibility score > 95

[ ] < 3 second initial load

---

## ✅ CRITICAL CHECKLIST

### Before Starting Week 1

[ ] Clone repository

[ ] Install dependencies

[ ] Review PRD & WBS

[ ] Set up development environment

[ ] Connect to MongoDB

[ ] Test local development

### Before Week 2 Ends

[ ] M1: 5 authentication tasks deployed to staging

[ ] M2: Login/Register/Password Reset UI complete

[ ] API documentation updated

[ ] Both can demonstrate auth flow

### Before Week 4 Ends

[ ] M1: All donation APIs complete

[ ] M2: All donation UI complete

[ ] Integration tests passing

[ ] Users can create & request donations

### Before Week 6 Ends

[ ] M1: All notifications/chat APIs complete

[ ] M2: All notification UIs complete

[ ] Real-time features tested

### Before Week 8

[ ] All tests passing

[ ] Security audit complete

[ ] Performance benchmarks met

[ ] Ready for production

---

## 🚨 COMMON BLOCKERS & SOLUTIONS

### "M1's API is not ready for M2 to integrate"

Solution: Use mock data while M1 finishes. M2 can build UI separately.

### "Database queries are slow"

Solution: Don't wait! Add indexes from day 1. M1 must monitor performance continuously.

### "API and Frontend versions mismatch"

Solution: Maintain API versioning (/api/v1/). Document breaking changes.

### "Security vulnerabilities found late"

Solution: Run security checks daily. Use OWASP guidelines from the start.

### "Testing coverage is low"

Solution: Write tests as you code, not after. Aim for 10%+ per sprint.

---

## 📞 COMMUNICATION SCHEDULE

### Daily Standup ⏰

Time: 10:00 AM (15 minutes)

Topics: Yesterday's work, today's plan, blockers

### Weekly Review 🗣️

Time: Friday 2:00 PM (30 minutes)

Topics: Demo features, discuss risks, plan next week

### PR Review 🔍

Target: 24 hours turnaround

Rule: All tests must pass before merge

### Slack/Discord

Use for: Quick questions, quick wins, blocker alerts

---

## 📚 DOCUMENTATION LOCATIONS

| Document | Location | Owner | Purpose |

|----------|----------|-------|---------|

| PRD (This Project) | `/PRD.md` | M1 to maintain | Requirements & vision |

| Work Breakdown | `/WORK_BREAKDOWN_STRUCTURE.md` | Both | Task details |

| API Documentation | `backend/docs/API.md` | M1 | API endpoints |

| Component Library | `frontend/COMPONENTS.md` | M2 | UI components |

| Database Schema | `backend/docs/SCHEMA.md` | M1 | Data structure |

| Deployment Guide | `/DEPLOYMENT.md` | M1 | How to deploy |

| Architecture | `backend/docs/ARCHITECTURE.md` | M1 | System design |

---

## 🎓 QUICK LEARNING RESOURCES

### For M1 (Backend)

Express.js: https://expressjs.com/

MongoDB: https://docs.mongodb.com/

JWT: https://jwt.io/

API Design: https://www.restfulapi.net/

Security: https://owasp.org/

### For M2 (Frontend)

React: https://react.dev/

Vite: https://vitejs.dev/

React Router: https://reactrouter.com/

Axios: https://axios-http.com/

CSS: https://web.dev/learn/css/

---

## 🚀 DEPLOYMENT CHECKLIST

### Staging (Week 6)

[ ] Backend deployed to staging server

[ ] Frontend deployed to staging CDN

[ ] Database backups configured

[ ] Monitoring & alerts set up

[ ] Team given staging credentials

### Production (Week 8)

[ ] All tests passing

[ ] Security review completed

[ ] Performance benchmarks met

[ ] Monitoring dashboards live

[ ] On-call rotation established

[ ] Rollback plan documented

---

## 💡 TIPS FOR SUCCESS

### For M1

**Database First:** Design your schema well before coding

**API Contracts:** Define API structure before implementing

**Error Handling:** Return consistent error responses

**Logging:** Log everything for debugging

**Performance:** Test with realistic data volumes

**Documentation:** Document as you code

### For M2

**Component First:** Break UI into reusable components

**Responsive Design:** Mobile-first approach

**API Integration:** Mock APIs first, connect later

**Accessibility:** Build a11y into every component

**Performance:** Lazy load, code split, optimize images

**Testing:** Test user interactions, not implementation

### For Both

**Communication:** Overcommunicate, especially on blockers

**Code Reviews:** Review each other's code (learn together)

**Version Control:** Small, frequent commits

**Automation:** Set up CI/CD from the start

**Monitoring:** Set up alerts early

**User Feedback:** Get feedback on features early

---

## 📞 WHEN TO ESCALATE

### Escalate to Project Manager If:

Task will take 50%+ more time than estimated

External dependency blocking progress

Need to change scope/timeline

Resource constraint discovered

Team conflict or morale issue

### Escalate to Tech Lead If:

Architectural decision needed

Technical debt discovered

Performance issues blocking feature

Security vulnerability found

Third-party service integration failing

---

## 🎉 LAUNCH CHECKLIST (Week 8)

### Day Before Launch

[ ] Final smoke tests passed

[ ] Backups verified

[ ] Monitoring dashboards ready

[ ] On-call team briefed

[ ] Rollback plan shared

[ ] Team celebrates! 🎊

### Launch Day

[ ] 5 min: Final check

[ ] 10 min: Deploy to production

[ ] 30 min: Monitor closely

[ ] 2 hours: Heavy monitoring

[ ] 24 hours: Stability check

---

## 📝 NOTES

**Total Project:** ~450 hours of development

**Each Team Member:** ~200-250 hours

**Per Week:** ~50-60 hours average

**Sprint Length:** 2 weeks per phase

---

Remember: 🌟 "The best code is code that gets shipped!"

Good luck! 🚀